## County Summary
County (Population) - Threshold |  | FEMA Inspector | Emergency Work |  | Permanent Work |  |  |  |  | Total
Rock County (163,687) - $795,518.82 |  | Jessica Price | 947619.0681 |  | 10085684 |  |  |  |  | 11033303.0681
Applicant | Type | Status | A | B | C | D | E | F | G | Applicant Total
County of Rock | County | Complete | 11500 | 10400 | 199000 |  |  |  | 10000 | 230900
City of Beloit | City | Complete | 50455 | 11933 | 5300 |  | 26500 |  |  | 94188
City of Janesville | City | Complete | 208000 | 7995 | 699800 | 1055000 | 15000 | 5216000 | 775000 | 7976795
Township of Bradford | Municipality | Complete | 17500 |  | 29500 |  |  |  |  | 47000
Township of Center | Municipality | Complete | [7 empty] | 0
Township of Fulton | Municipality | Complete | 5000 | 22880 | 4500 |  |  |  |  | 32380
Township of Harmony | Municipality | Complete |  |  | 16248 |  |  |  |  | 16248
Township of Janesville | Municipality | Complete | 5000 | 5700 | 456995 |  |  |  |  | 467695
Township of Johnston | Municipality | Complete | [7 empty] | 0
Township of La Prairie | Municipality | Complete | 7500 | [6 empty] | 7500
Township of Milton | Municipality | Complete | 6000 | 11000 | 13241 |  |  |  |  | 30241
Township of Plymouth | Municipality | Complete | 13475 |  | 12550 |  |  |  |  | 26025
Township of Porter | Municipality | Complete | [7 empty] | 0
Township of Rock | Municipality | Complete | 36750 | 19200 | 28750 |  |  |  |  | 84700
Township of Spring Valley | Municipality | Complete |  |  | 24500 |  |  |  |  | 24500
Township of Turtle | Municipality | Complete | 0 | [6 empty] | 0
Township of Orfodville | Municipality | Complete |  |  |  |  | 12500 |  |  | 12500
Department of Transportation | Government | Complete | 221500 | 56500 | [5 empty] | 278000
National Guard | Government | Complete |  | 152815.1381 | [5 empty] | 152815.1381
First Lutheran Church | PNP | Complete | 66515.93 | [6 empty] | 66515.93
Janesville School District | Government | Complete |  |  |  |  | 1485300 |  |  | 1485300
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Deduction Comments
Applicant | Comments
County of Rock | Cat A: Estimated $11,500 for debris removal from county roads and ROWs. Validated: $11,500 based on photos and summaries. Cat B: Estimated $10,400 for road closures, barricades and debris clearance from roads. Validated: $10,400 based on summaries. Cat C: Estimated $199,000 for 22 road sites. Applicant provided photos showing road, shoulder, ditch and culvert washouts and damages. Validated: $199,000 based on photos and summaries. Cat G: Estimated $10,000 for washout of pedestrian bridge. Validated: $10,000 based on photos and summaries.
City of Beloit | Cat A: Estimated $50,455 in waterway vegetative debris removal caught in a pedestrian bridge and floating docks as well as residential debris removal. RFI for cost documentation, cost breakdown provided in RFI response. Validated $50,455 using photos, cost breakdown of fa labor and equipment and contractor costs Cat B: Estimated $11,933 in emergency protective measures including sandbagging and emergency response to flooded homes. Validated $11,933 using cost breakdowns Cat C: Estimated $20,800 in road shoulder washouts. Reduced $15,500 for two sites listed as Major Collectors and not eligible for PA. Validated: $5,300 using photos, locations and damage descriptions. Cat E: Estimated $26,500 in damages to a river front pavillion. RFI sent for supporting documentation for cost estimates and insurance. Applicant states no insurance on the building due to it being in a floodplain. Validated $26,500 using photos, cost breakdown and narrative. Cat G: Estimated $2,000 in damages to pavillion floating dock. Reduced: $2,000 for not meeting FY26 minimum project threshold of $4,100. Validated: $0
City of Janesville | Cat A: Estimated $508,000 for debris removal activities for 26 sites/areas. The City removed vegetative debris, sediment, rocks, and other disaster debris from public ROWs, trails, public property, drainage channels, culverts and bridges. Applicant included 2 sites for $300,000 for flooding damage to First Lutheran Church and Washington Elementary School. These are separate entities. Creating additional applicant entries in Chart A for the PNP and School District. Reduced: $300,000 for flood damages to school and pnp. Validated: $208,000 based on debris photos, locations and cost summaries. Cat B: Estimated $7,995 for costs related sandbagging, floodfighting, EOC and other emergency measures. Validated: $7,995 based on descriptions and cost summaries. Cat C: Estimated $1,499,800 for road washouts, sinkholes, culvert failures, ditch damages, shoulder washouts, embankment erosion, riprap washout, road drainage damage and road sign damages across the City. Applicant submitted 34 damage sites (removed 5 from the iniital submission of 39 sites during PDA). Reduced: $800,000 for Ruger Ave and Palmer Drive Bridge because the roads are federal-aid roads and ineligible for PA. Validated: $699,800 based on photos and summaries provided. Cat D: Estimated: $1,755,000 for various damages to drainage facilities including washout of riprap and embankment protections, culvert failures, outfall damages, storm sewer pipe damages, blocked/plugged culverts and intake structures and erosion. Included in this estimate is $500,000 estimated damages to Greenbelt Drainage System (engineered system of channels, basins, outfalls, culverts, etc) and $1,000,000 estimated for debris and shoreline damages to Springbrook and Blackhawk Creeks. Conducted site visits to Greenbelt and Springbrook and Blackhawk Creeks, and Applicnat provided detailed damage photos for remaining sites. Site visits showed major washouts around culverts, trails, and gabion baskets along creek, and significant vegetative debris blocking channels and culverts. Reduced: $700,000 for shoreline grading, seeding and stabilization along Springbrook and Blackhawk Creeks. Site visits showed mostly unimproved embankments and natural land, without evidence of maintained improvements. Able to validate debris blocking creeks and inlets, and damage to existing gabion baskets. Also able to validate damages to Greenbelt through site visits. Validated: $1,055,000 based on photos, site inspections and cost summaries. Cat E: Estimated: $7,015,000 for flood damage to 4 buildings: Washington Elementary School, First Lutheran Church, Janesville Fire Training Center and City Building. Washington Elementary School is responsibility of Janesville School District, not the City and First Lutheran Church is responsibility of PNP. Reduced: $7,000,000 for the school and PNP damages and addressing those costs under their own separate applicant entries on the Chart A. Validated: $15,000 for city building and fire training center based on photos and cost summaries. Cat F: Estimated: $6,539,600 for damages to City's storm sewer system; increased sewage treatment costs; and traffic light signal damages. Applicant estimating 40% of storm sewer system needs to be cleaned of debris and 90% of the outfalls need clearance and repairs. City just completed its annual storm sewer cleaning and based estimates for cleaning on those maintenance contracts. Conducted site visits on a sampling of outfalls and inlets from all areas of the City. Outfalls showing massive washout damages and vegetative and sediment debris throughout the pipes we sampled. Inlets similarly show visible vegetative and sediment debris in pipes. The Applicant estimating an average of $5,000 of debris and repair work per outfall. CEFs completed for a couple of the sites visited, showed damages and costs to those would be significantly higher. Thus, the low average estimate of $5,000 is reasonable. Reduced: $1,320,000 for number of outfalls to be repaired. Removed approximately 300 outfalls from original estimate of 930 based on GIS mapping and discussions with the Applicant and State regarding areas of city impacted and legal responsibility. Reduced: $3,600 for increased operating costs of having to treat more gallons of water than typical due to flooding. These increased costs not tied to eligible emergency protective measure, just increased usage of its normal service. Validated: $5,216,000 based on system maps, photos, site visits, and cost estimates based on historical costs. Cat G: Estimated: $850,000 for 26 park sites, including trail washouts, walking bridge damages and other park washouts. Reduced: $75,000 for road damages claimed to site 51451 (Cemetery Road) because damage photos show signifcant alligator cracking, potholes and prior deterioration. Validated: $775,000 based on photos, site visits and cost summaries.
Township of Bradford | Cat A: Estimated $17,500 for vegetative debris removal from roads. Validated $17,500 using photos, location maps and damage descriptions. Cat B: Estimated $2,000 in barricading of flooded roads. Reduced: $2,000 for not meeting FY26 minimum project threshold of $4,100. Validated: $0 Cat C: Estimated $29,500 in road shoulder, base and surface washouts at 9 sites. Validated $29,500 using photos, damage descriptions and cost estimates.
Township of Center | Cat C: Estimated $2,500 for one gravel road washout site. Originally 7 sites were identified, an RFI was sent for cost clarification and applicant withdrew the other 6 sites that were mislabled under the wrong applicant. Updated costs provided for 1 site. Reduced: $2,500 for not meeting FY26 minimum project threshold of $4,100. Validated $0
Township of Fulton | Cat A: Estimated: $5000 for debris removal. Validated: $5000 from applicant provided estimates Cat B: Estimated: $22,880 for sandbagging operations, baricading, monitoring and EOC operations. Validated: $22,880 based on applicant provided costs Cat C: Estimated: $4,500 for shoulder damages and washouts. Validated $4500 based on applicant provided costs and estimates
Township of Harmony | Cat A: Estimated: $3,000 for vegetative debris removal from roads and ditches. Reduced: $3,000 due to costs not meeting the minimum project threshold of $4,100. Cat B: Estimated: $2,100 for barricading and road signs. Reduced: $2,100 due to the costs not meeting the minimum project threshold of $4,100. Cat C: Estimated: $16,248 for road washouts and damages. Validated: $16,248 from applicant documentation.
Township of Janesville | Cat A: Estimated $5,000 for debris removal from culverts, ditches and road shoulders. Applicant initially claimed $2,500, but also had two debris sites listed under Cat C that have been added to the Cat. A. Validated: $5,000 based on photos and summaries. Cat B: Estimated $5,700 for sandbagging and road closures/barricades. Validated: $5,700 based on summaries. Cat C: Estimated $459,495 for 41 road sites. Damages include road, shoulder and ditch washouts and Rockport Bridge collapse. Applicant included two debris sites in Cat C (55562 ($1,500) and 59088 ($1,000)). Reduced $2,500 from Cat C for debris sites and added to Cat A. Applicant also claiming $400,000 for complete collapse of Rockport Bridge. Past bridge inspection reports list road as local road and FEMA engineers validated that $400,000 to replace that size of bridge was reasonable. Validated $456,995 based on photos, bridge inspection reports and FEMA engineers.
Township of Johnston | Cat C: Estimated $4,000 - for road damages and shoulder washout. Reduced: $4,000 due to the costs not meeting the minimum project threshold.
Township of La Prairie | Cat A: Estimated $7,500 for vegetative debris removal from roads and a culvert. Validated $7,500 from applicant documents. Cat B: Estimated $1,000 for road barricades and road signs. Reduced: $1,000 due to the costs not meeting the minimum project threshold of $4,100 Cat C: Estimated $3,000 for road washout near a culvert. Reduced $3,000 ( including $1,000 due to ineligible costs of unidentified road damage) and the costs not meeting the minimum project threshold of $4,100.
Township of Milton | Cat A: Estimated $6,000 for debris removal. Validated $6,000 from applicant documentation. Cat B: Estimated $11,000 for sandbagging, road barricading, and monitoring. Validated $11,000 from applicant documentation. Cat C: Estimated $16,741 for road damage (shoulder and culvert washout). RFI was issued for 4 Cat C sites requesting specific damages to be identified. Applicant withdrew 4 Cat C sites. Reduced $500 due to damages on a major collector . Validated: $13,241 based on applicant documentation Cat E: Estimated $250 for building damages/contents. Reduced: $250 for not meeting the minimum project threshold of $4,100
Township of Plymouth | Cat A: Estimated $13,475 for jurisdiction-wide debris removal. Validated: $13,475 based on applicant documentation. Cat B: Estimated $2,800 for emergency protective measures. Reduced $2,800 for not meeting FY26 minimum project threshold of $4,100. Cat C: Estimated 12,550 for washout and road damages. Validated $12,550 from applicant documentation Cat E: Estimated $30,000 for damages to building equipment caused by flooding. RFI sent to applicant to ask for insurance, a cost breakdown of damages and for any other damages. Reduced $30,000 due to no response to RFI and no specific damages identified by applicant
Township of Porter | Applicant is requesting withdrawal.
Township of Rock | Cat A: Estimated: $39,250 for debris removal. Reduced: $2,500 due to ineligible costs for debris removed from a cemetery Validated: $36,750 based on applicant documentation. Cat B: Estimated: $19,200 for sandbagging (transport, production and disposal) and barricading and signage. Validated $19,200 based on applicant documentation. Cat C: Estimated: $437,750 for washout to road, shoulders and culverts. Reduced: $409,000 due to damages on major collectors Rockport Rd and Plymouth Church Rd. Validated: $28,750 based on the applicant documentation Cat G: Estimated: $2,400 for damages to a fence and headstones. RFI sent to applicant to separate the costs of damages. Applicant provided the requested breakdown but it did not add additional costs. Reduced: $2400 due to the costs not meeting the minimum project threshold of $4,100.
Township of Spring Valley | Cat B: Estimated $1,400 for barricading and signage. Reduced: $1,400 due to costs not meeting minimum project threshold. Cat C: Estimated $24,500 for road and shoulder damages. Validated: $24,500 based on applicant documentation.
Township of Turtle | Cat A: Estimated $975 for debris removal. Reduced $975 due to the project cost not meeting the minimum project threshold.
Township of Orfodville | Cat B: Estimated $1,014.80 for sandbagging and barricading. Reduced: $1,014.80 due to the costs not meeting the minimum project threshold Cat E: Estimated $12,500 for insurance deductible for building damages. RFI sent to applicant for insurance documents for the building. Insurance documents couldn't be provided in short timeline, applicant provided confirmation of deductibles via email from insurance agent. Validated: $12,500
Department of Transportation | Cat A: Estimated: $221,500 for debris removal due to flooding. Validated: $221,500 with applicant provided summary sheets. Cat B: Estimated: $56,500 for traffic control cost due to road closure and detours from flooding. Validated: $56,500 with applicant provided summary sheets. Cat C: Estimated: $552,500 for road damages due to flooding. Reduced: $552,500 road is FHWA eligible. Validated: $0
National Guard | Cat B: Estimated: $152,815.14 for sandbaggin and high water assistance due to flooding. Validated: $152,815.14 using applicant provided summary sheets.
First Lutheran Church | Cat A: Estimated: $66,515.93 for debris clean up from flood damaged building. Validated: $66,515.93 based on detailed cost summary and flooding and damage photos showing debris. Cat E: Estimated: $5,000,000 for flooding damages to building and mechanical equipment. Building flooded 4 feet in lower level and damaged boiler room, equipment, kitchen, cafeteria and all electrical/mechanical. Applicant's insurance company determined only $10,000 of coverage for the flooding damage. However, PNP is non-crtical, essential social services and therefore would need to apply to SBA before eligible for permanent restoration under FEMA. Reduced: $5,000,000 due to PNP needing to file with SBA first. Validated: $0.
Janesville School District | Cat E: Estimated: $2,000,000 for flooding damage to Washington Elementary School. The City stated that the Applicant's insurance policy only covers up to $150,000 of flood damage. Applicant provided letter and copy of check received from insurance company for the $150,000 of insurance coverage. No information was provided to validate the cost estimate. FEMA engineer prepared CEF for flood damage and clean up totaling $1,635,300. Reduced: $514,700 due to CEF cost estimate and $150,000 of covered loss. Validated: $1,485,300 based on videos, photos and articles showing flood damge to school, CEF prepared by FEMA engineer and insurance coverage.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Notes (hidden)
Created by Charles Annerino
Charles.Annerino@fema.dhs.gov

## County Population and Threshold (hidden)
Wisconsin (5,893,718) - $11,433,813
County (Population) - Threshold | Team Leads
Adams County (20,654) - $100,378.44 | Anessa Jones | Adams County | 20654 | 20,654 | 100378.44 | $100,378.44
Ashland County (16,027) - $77,891.22 | Angel Felix | Ashland County | 16027 | 16,027 | 77891.22 | $77,891.22
Barron County (46,711) - $227,015.46 | Bassam Efein | Barron County | 46711 | 46,711 | 227015.46 | $227,015.46
Bayfield County (16,220) - $78,829.20 | Catherine Warren | Bayfield County | 16220 | 16,220 | 78829.2 | $78,829.20
Brown County (268,740) - $1,306,076.40 | Connor Blevins | Brown County | 268740 | 268,740 | 1306076.4 | $1,306,076.40
Buffalo County (13,317) - $64,720.62 | James Cathey | Buffalo County | 13317 | 13,317 | 64720.62 | $64,720.62
Burnett County (16,526) - $80,316.36 | Javon Cotton | Burnett County | 16526 | 16,526 | 80316.36 | $80,316.36
Calumet County (52,442) - $254,868.12 | Jessica Price | Calumet County | 52442 | 52,442 | 254868.12 | $254,868.12
Chippewa County (66,297) - $322,203.42 | Lindsay LaMarca | Chippewa County | 66297 | 66,297 | 322203.42 | $322,203.42
Clark County (34,659) - $168,442.74 | Maxwell Novoselac | Clark County | 34659 | 34,659 | 168442.74 | $168,442.74
Columbia County (58,490) - $284,261.40 | Natalie Schrader | Columbia County | 58490 | 58,490 | 284261.4 | $284,261.40
Crawford County (16,113) - $78,309.18 | Richard Chiarello | Crawford County | 16113 | 16,113 | 78309.18 | $78,309.18
Dane County (561,504) - $2,728,909.44 | Roopak Hanna | Dane County | 561504 | 561,504 | 2728909.44 | $2,728,909.44
Dodge County (89,396) - $434,464.56 | Seth Crawford | Dodge County | 89396 | 89,396 | 434464.56 | $434,464.56
Door County (30,066) - $146,120.76 | Shawana Thomas | Door County | 30066 | 30,066 | 146120.76 | $146,120.76
Douglas County (44,295) - $215,273.70 | Tracie Smith | Douglas County | 44295 | 44,295 | 215273.7 | $215,273.70
Dunn County (45,440) - $220,838.40 |  | Dunn County | 45440 | 45,440 | 220838.4 | $220,838.40
Eau Claire County (105,710) - $513,750.60 |  | Eau Claire County | 105710 | 105,710 | 513750.6 | $513,750.60
Florence County (4,558) - $22,151.88 |  | Florence County | 4558 | 4,558 | 22151.88 | $22,151.88
Fond Du Loc County (104,154) - $506,188.44 |  | Fond Du Loc County | 104154 | 104,154 | 506188.44 | $506,188.44
Forest County (9,179) - $44,609.94 |  | Forest County | 9179 | 9,179 | 44609.94 | $44,609.94
Grant County (51,938) - $252,418.68 |  | Grant County | 51938 | 51,938 | 252418.68 | $252,418.68
Green County (37,093) - $180,271.98 |  | Green County | 37093 | 37,093 | 180271.98 | $180,271.98
Green Lake County (19,018) - $92,427.48 |  | Green Lake County | 19018 | 19,018 | 92427.48 | $92,427.48
Iowa County (23,709) - $115,225.74 |  | Iowa County | 23709 | 23,709 | 115225.74 | $115,225.74
Iron County (6,137) - $29,825.82 |  | Iron County | 6137 | 6,137 | 29825.82 | $29,825.82
Jackson County (21,145) - $102,764.70 |  | Jackson County | 21145 | 21,145 | 102764.7 | $102,764.70
Jefferson County (84,900) - $412,614.00 |  | Jefferson County | 84900 | 84,900 | 412614 | $412,614.00
Juneau County (26,718) - $129,849.48 |  | Juneau County | 26718 | 26,718 | 129849.48 | $129,849.48
Kenosha County (169,151) - $822,073.86 |  | Kenosha County | 169151 | 169,151 | 822073.86 | $822,073.86
Kewaunee County (20,563) - $99,936.18 |  | Kewaunee County | 20563 | 20,563 | 99936.18 | $99,936.18
La Cross County (120,784) - $587,010.24 |  | La Cross County | 120784 | 120,784 | 587010.24 | $587,010.24
Lafayette County (16,611) - $80,729.46 |  | Lafayette County | 16611 | 16,611 | 80729.46 | $80,729.46
Langlade County (19,491) - $94,726.26 |  | Langlade County | 19491 | 19,491 | 94726.26 | $94,726.26
Lincoln County (28,415) - $138,096.90 |  | Lincoln County | 28415 | 28,415 | 138096.9 | $138,096.90
Manitowoc County (81,359) - $395,404.74 |  | Manitowoc County | 81359 | 81,359 | 395404.74 | $395,404.74
Marathon County (138,013) - $670,743.18 |  | Marathon County | 138013 | 138,013 | 670743.18 | $670,743.18
Marinette County (41,872) - $203,497.92 |  | Marinette County | 41872 | 41,872 | 203497.92 | $203,497.92
Marquette County (15,592) - $75,777.12 |  | Marquette County | 15592 | 15,592 | 75777.12 | $75,777.12
Menominee County (4,255) - $20,679.30 |  | Menominee County | 4255 | 4,255 | 20679.3 | $20,679.30
Milwaukee County (939,489) - $4,565,916.54 |  | Milwaukee County | 939489 | 939,489 | 4565916.54 | $4,565,916.54
Monroe County (46,274) - $224,891.64 |  | Monroe County | 46274 | 46,274 | 224891.64 | $224,891.64
Oconto County (38,965) - $189,369.90 |  | Oconto County | 38965 | 38,965 | 189369.9 | $189,369.90
Oneida County (37,845) - $183,926.70 |  | Oneida County | 37845 | 37,845 | 183926.7 | $183,926.70
Outagamie County (190,705) - $926,826.30 |  | Outagamie County | 190705 | 190,705 | 926826.3 | $926,826.30
Ozaukee County (91,503) - $444,704.58 |  | Ozaukee County | 91503 | 91,503 | 444704.58 | $444,704.58
Pepin County (7,318) - $35,565.48 |  | Pepin County | 7318 | 7,318 | 35565.48 | $35,565.48
Pierce County (42,212) - $205,150.32 |  | Pierce County | 42212 | 42,212 | 205150.32 | $205,150.32
Polk County (44,977) - $218,588.22 |  | Polk County | 44977 | 44,977 | 218588.22 | $218,588.22
Portage County (70,377) - $342,032.22 |  | Portage County | 70377 | 70,377 | 342032.22 | $342,032.22
Price County (14,054) - $68,302.44 |  | Price County | 14054 | 14,054 | 68302.44 | $68,302.44
Racine County (197,727) - $960,953.22 |  | Racine County | 197727 | 197,727 | 960953.22 | $960,953.22
Richland County (17,304) - $84,097.44 |  | Richland County | 17304 | 17,304 | 84097.44 | $84,097.44
Rock County (163,687) - $795,518.82 |  | Rock County | 163687 | 163,687 | 795518.82 | $795,518.82
Rusk County (14,188) - $68,953.68 |  | Rusk County | 14188 | 14,188 | 68953.68 | $68,953.68
St.Croix County (93,536) - $454,584.96 |  | St.Croix County | 93536 | 93,536 | 454584.96 | $454,584.96
Sauk County (65,763) - $319,608.18 |  | Sauk County | 65763 | 65,763 | 319608.18 | $319,608.18
Sawyer County (18,074) - $87,839.64 |  | Sawyer County | 18074 | 18,074 | 87839.64 | $87,839.64
Shawano County (40,881) - $198,681.66 |  | Shawano County | 40881 | 40,881 | 198681.66 | $198,681.66
Sheboygan County (118,034) - $573,645.24 |  | Sheboygan County | 118034 | 118,034 | 573645.24 | $573,645.24
Taylor County (19,913) - $96,777.18 |  | Taylor County | 19913 | 19,913 | 96777.18 | $96,777.18
Trempealeau County (30,760) - $149,493.60 |  | Trempealeau County | 30760 | 30,760 | 149493.6 | $149,493.60
Vernon County (30,714) - $149,270.04 |  | Vernon County | 30714 | 30,714 | 149270.04 | $149,270.04
Vilas County (23,047) - $112,008.42 |  | Vilas County | 23047 | 23,047 | 112008.42 | $112,008.42
Walworth County (106,478) - $517,483.08 |  | Walworth County | 106478 | 106,478 | 517483.08 | $517,483.08
Washburn County (16,623) - $80,787.78 |  | Washburn County | 16623 | 16,623 | 80787.78 | $80,787.78
Washington County (136,761) - $664,658.46 |  | Washington County | 136761 | 136,761 | 664658.46 | $664,658.46
Waukesha County (406,978) - $1,977,913.08 |  | Waukesha County | 406978 | 406,978 | 1977913.08 | $1,977,913.08
Waupaca County (51,812) - $251,806.32 |  | Waupaca County | 51812 | 51,812 | 251806.32 | $251,806.32
Waushara County (24,520) - $119,167.20 |  | Waushara County | 24520 | 24,520 | 119167.2 | $119,167.20
Winnebago County (171,730) - $834,607.80 |  | Winnebago County | 171730 | 171,730 | 834607.8 | $834,607.80
Wood County (74,207) - $360,646.02 |  | Wood County | 74207 | 74,207 | 360646.02 | $360,646.02